REPORT 1

RESEARCH PROPOSAL

Vehicle Behavior Analysis Using Real-World Trajectory Data

Revised full-dataset proposal · 10-week RBL project

Group 3 | Class IS1904 | FPT University HCM

Lê Hữu Đại (SE184118), Nguyễn Quốc Cường (SE193612), Thái Nhật Hoàng (SE196438), Đặng Quang Phú (SE184468), Tô Ngọc Anh Tuấn (SE190681)

# 1. Group Information

| Content | Description |
| --- | --- |
| Group name | Group 3 |
| Project title | Vehicle Behavior Analysis Using Real-World Trajectory Data |
| Class | IS1904 |
| Course | DTA301 – Data Analysis |
| RBL theme | Data-driven Analytics for Drone / UAV / Autonomous Systems |
| Member 1 | Lê Hữu Đại – SE184118 – Team Leader |
| Member 2 | Nguyễn Quốc Cường – SE193612 – Data Engineer |
| Member 3 | Thái Nhật Hoàng – SE196438 – Model Developer |
| Member 4 | Đặng Quang Phú – SE184468 – Report & Presentation Lead |
| Member 5 | Tô Ngọc Anh Tuấn – SE190681 – Data Analyst |

# 2. Project Title

Vehicle Behavior Analysis Using Real-World Trajectory Data

The official research topic identifies the analysis focus (vehicle behavior) and the data source (real-world trajectory data). The full multi-city SinD scope, unsupervised clustering design, and interpretable behavior-profile objective are specified in the research questions and methodology.

# 3. Research Background and Problem

Signalized intersections produce diverse vehicle responses: some cars maintain speed, others stop and restart, adjust speed repeatedly, brake, or accelerate strongly. Autonomous-driving simulation and behavior-aware prediction require more than object detection; they require interpretable evidence about how complete trajectories differ.

The SinD dataset provides drone-observed, real-world trajectories from signalized intersections. By transforming frame-level observations into trajectory-level behavior features, the project can discover profiles without predefined behavior labels and support structured review of queueing, speed adjustment, and high-dynamic maneuvers.

Decision-support objective Summarize millions of raw observations into explainable behavior profiles that help analysts decide which traffic contexts and trajectories should be inspected first. The project does not claim to predict crash probability or permanent driver type.

# 4. Research Questions

| Question type | Content |
| --- | --- |
| Main RQ | What distinct passenger-car behavior profiles emerge from real-world trajectories across signalized intersections, and how consistently can these profiles be interpreted across recordings and cities? |
| Sub-RQ1 | Which trajectory-level speed, acceleration, braking, jerk, and stopping features most clearly distinguish the discovered profiles? |
| Sub-RQ2 | Which preprocessing and clustering approach provides the best balance of internal quality, complete coverage, stability, cross-context transferability, and interpretability? |

# 5. Project Objectives

1. Inventory and describe the full SinD package across multiple cities and recordings.

2. Build a reproducible frame-to-trajectory cleaning and feature-engineering pipeline.

3. Perform EDA to evaluate distributions, outliers, redundancy, and city/recording effects.

4. Construct a simple K-Means baseline and compare multiple clustering families.

5. Evaluate models using internal metrics, coverage, seed and bootstrap stability, and cross-city/cross-recording validation.

6. Interpret final profiles in physical units and use Tianjin metadata only for post-cluster contextual analysis.

# 6. Dataset Used

| Content | Description |
| --- | --- |
| Dataset name | Signalized Intersection Dataset (SinD) – full academic package |
| Source | Official SOTIF-AVLab SinD project; author-provided academic-access package |
| Public link | Official SinD repository/paper; private download credentials are not reproduced |
| Cities / recordings | 4 cities: Changchun, Chongqing, Tianjin, Xi’an; 56 recordings |
| Initial vehicle rows | 12,052,293 frame-level vehicle observations |
| Initial vehicle trajectories | 30,369 trajectories; 20,704 passenger-car trajectories |
| Data type | Time-series / trajectory / sensor-log style CSV data |
| Usage condition | Academic, non-commercial use; citation required; raw full dataset must not be redistributed |
| Reason selected | Real-world multi-context intersection trajectories support interpretable unsupervised behavior discovery and external context validation. |

# 7. Planned Method

| Component | Planned approach |
| --- | --- |
| Problem type | Unsupervised clustering |
| Analysis unit | One complete passenger-car trajectory |
| Baseline | K-Means on a reduced PCA representation |
| Comparison models | MiniBatch K-Means, Gaussian Mixture, Agglomerative clustering, DBSCAN, and HDBSCAN |
| Core inputs | 10 features covering speed, longitudinal dynamics, variability, jerk, stop transitions, and stopped-time ratio |
| Preprocessing candidates | Winsorization vs. raw tails; StandardScaler vs. RobustScaler; PCA retaining at least 90% variance |
| Internal metrics | Silhouette, Davies–Bouldin, Calinski–Harabasz, cluster balance, coverage/noise |
| Validation | Repeated seeds, bootstrap/resampling, leave-one-city-out, leave-one-recording-out, profile semantics |
| Interpretation | Original-unit profile medians, centroid-nearest trajectories, city prevalence, Tianjin CrossType and signal-violation context |
| Tools | Python, pandas, NumPy, SciPy, scikit-learn, Matplotlib, Jupyter Notebook |

## Planned Research Pipeline

Workflow Raw recording ZIPs → schema and quality audit → passenger-car filtering → unique trajectory IDs → 10 behavior features → EDA → preprocessing benchmark → PCA → clustering benchmark → stability and cross-context validation → final interpretation.

## Ethical and Scope Controls

Do not redistribute the restricted full SinD package or private access credentials.

Do not use traffic-signal labels as clustering inputs; preserve the unsupervised design.

Do not label clusters as safe/unsafe drivers or claim causal crash risk.

Report city and recording sensitivity instead of presenting all contexts as identical.

# 8. 10-Week Implementation Plan

| Week | Main work | Responsible |
| --- | --- | --- |
| Week 3 | Define problem, RQs, dataset scope, literature, and proposal | Whole group |
| Week 4 | Dataset inventory, schema checks, cleaning, data dictionary, EDA | Cường, Tuấn |
| Week 5 | Trajectory feature engineering, preprocessing, K-Means baseline | Hoàng, Đại |
| Weeks 6–7 | Preprocessing/PCA benchmark, visualizations, stability design | Đại, Hoàng, Phú |
| Week 8 | Model comparison, bootstrap, density benchmarks, error analysis | Hoàng, Cường, Tuấn |
| Week 9 | Cross-city/recording validation and profile interpretation | Whole group |
| Week 10 | Final paper, slide deck, GitHub package, reproducibility review | Phú, Tuấn, Đại |

# 9. Role Distribution

| Role | Main responsibility | Member |
| --- | --- | --- |
| Team Leader | Coordinate scope, consolidate reports, track progress, and ensure consistency. | Lê Hữu Đại – SE184118 |
| Data Engineer | Organize raw recordings, validate schemas, implement cleaning and data dictionary. | Nguyễn Quốc Cường – SE193612 |
| Model Developer | Build and evaluate clustering models and validation experiments. | Thái Nhật Hoàng – SE196438 |
| Report & Presentation Lead | Prepare reports, citations, slides, and presentation materials. | Đặng Quang Phú – SE184468 |
| Data Analyst | Conduct EDA, visualization, interpretation, and contextual analysis. | Tô Ngọc Anh Tuấn – SE190681 |

# References

[1] Y. Xu et al., “SIND: A Drone Dataset at Signalized Intersection in China,” IEEE ITSC, 2022.

[2] J. Zhao et al., “Large Scale Autonomous Driving Scenarios Clustering with Self-supervised Feature Extraction,” arXiv:2103.16101, 2021.

[3] S. Bandyopadhyay et al., “Unsupervised Driving Behavior Analysis Using Representation Learning and Exploiting Group-Based Training,” arXiv:2205.07870, 2022.

[4] T. Kreutz et al., “Unsupervised Driving Event Discovery Based on Vehicle CAN-data,” arXiv:2301.04988, 2023.